## Sheet1
Date | Iteration 1.1 Modeling | External Dashboard | Iteration 1 Data Reports | Iteration 1.2 Modeling | Iteration 2 Causal Mapping | Addtl
2018-05-09 | - clean up SQL code - exclude CCI members and export new data set to CDSW. - contrast at least 3 training metrics from list: accuracy, kappa, F1, d', AUROC, AUPRC. - try penalizing either FN or FP - decide on the best metric to use in tran() given the business goal and potential class imbalance - generate best possible individual and ensemble models as well as LACE scores. - comment to make clear where the code may be improved or what drove choices in modeling. - generate html report with existing code. - post report to git |  | - Update Git data reports with info about data used in iteration 1.1 - examine 665 fields & the hospital inclusion set that Mary Mitchell sent. (Follow up on the Olivers' admit) - get HRA scores into HDFS and into data reports
2018-05-10 |  | development (1hr / day with BS)
2018-05-11
2018-05-14 |  | development (1hr / day with BS) | - Chase after potential social support predictors; extract from HRA subscore a Y-variable against which to model social support. Ask Leela to migrate data. |  |  | contrast members you reach through risk adjustment, care management, utilization management. [Engage UM, risk adjustment to see whether current model interests them, and if not find out what interests them and which iteration to include it in.]
2018-05-15
2018-05-16 |  |  | - get name of someone to contact about logisticare. Identify other transportation issues.
2018-05-17 | DELIVERY | - Nathalie to define fuzzy logic to end an inpatient stay, based on LOS distribution. (When we have Dx data, may be able to refine the logic.) - Nathalie to reproduce Brandon's Tableau work in order to familiarize herself with the tool. - Nathalie to suggest an overall design to the Workbook. | - talk with CM about how to ID which members/PPG/hospitals have care management (DOFR? Analyze pattern by PPG? By Hospital?)
2018-05-18
2018-05-21 |  | - Apply fuzzy logic to inpatient census. In long-term planning page: have a display of the daily census over time for I, ER, I+ER. In same-day action page: have a display of same-day census, pie'd ER, I, and gp'd by facility. | - Chase after data on CM access & ask for data migration | - Build against HRA scores models of social support.
2018-05-22 |  |  | -Consult with SMEs on why transportation is an issue (Amezcua?) and (who?) where data reside.
2018-05-23 |  |  | - Chase after transportation data & ask for data migration
2018-05-24 |  |  | - Update Git data reports with info about new data imported for the purpose of representing transp. and access to CM.
2018-05-25 |  |  | -how do you define health literacy through the data? Meet with Matt Pirritano to troubleshoot?
2018-05-29 |  | Assessment methodology | - Chase after Health Literacy data & ask for data migration | - Build [against what?] a model of failure to obtain transportation. Aletrnatively, aggregate together somehow the candidate predictors for such failure. |  | C-suite steering committee, data science
2018-05-30 |  | Feedback from CM | - Update Git data reports with info about new data imported for the purpose of representing health literacy. |  |  | Meeting with Marie London
2018-05-31 |  | Implement changes
2018-06-01 |  | DELIVERY |  |  | schedule the meeting
2018-06-04 |  | Collect data on usage and satisfaction. | -Get eConnect data. Update data reports with eConnect data. Work with Leela to expand data migration protocol to include new factors. | -Model health literacy [against what measure of a person's level of health literacy?]
2018-06-05
2018-06-06
2018-06-07
2018-06-08
2018-06-11 |  |  | DELIVERY | - Do pre-processing of the predictors in the training set. - Train models according to plan in Iteration 1.1 - Attempt a more complex ensemble model than majority vote. - Attempt clustering by Dx. [This will be Iteration 2's focus] - Format the report according to plan in iteration 1.1
2018-06-12
2018-06-13
2018-06-14 |  | REVIEW
2018-06-15
2018-06-18
2018-06-19
2018-06-20
2018-06-21 |  |  |  | DELIVERY
2018-06-22
2018-06-25 |  |  |  |  | Prep materials:The value of predictors that are already being used is assessed: Are they well operationalized? Do they affect the outcome as the experts expected (and if not, why not)? Are there new factors that may flesh out the existing map? If the initial priority set (health literacy, transportation, access to care management). This marks the beginning of Iteration 2 model.
2018-06-26
2018-06-27
2018-06-28
2018-06-29 |  |  |  |  | DELIVERY
Iteration 2: Iteration 2 aims to develop specific-cause models and to expand the set of predictive variables in response to the second causal mapping session. It also aims to start paring down the predictor set to those that may be accessed on admit day, from either eConnect or historical claims. July/August, 2018: • Expand predictor set to everything eConnect has to offer. Train separate models for each of the top 10 APR-DRGs. Try to reverse-engineer the 3M algorithm that leads to APR-DRG. • Begin work with a small group of domain experts on how to group diagnoses into clusters that may be modeled independently. Work “top-down” by asking experts what diagnoses are affected by the same variables. Work “bottom-up” by examining clustering among predictors, differences in time between discharge and readmission. • Train specialized models for each high-value diagnostic cluster. September, 2018: • Have a tried-and-true daily report to CM that brings value to that group. Quantify that value. • Plan transition toward using eConnect data for timelier predictions. • Hold 3rd causal mapping session to focus on a small number of high-value diagnoses and their corresponding models This will be the end of Iteration 2.